## Q3 Findings Register
ID | Severity | Confidence | Finding | Evidence | Remediation / disposition | Retest | Status
Q3-VA-001 | Critical aggregate scanner rating | Low until mapped | OCI VSS returned 1,000 records: 193 Critical, 649 High and 158 Medium. Only three records identify vulnerable packages; 997 have no package mapping. | OCI host scan completed 2026-08-11T01:13:39Z. | Do not present all 1,000 as confirmed vulnerabilities. Validate package presence/applicability. The three mapped High records concern host python3-pip/python3-wheel and ESM fix versions. Patch or remove them in an approved window. | Fresh scan required after host maintenance. | Open — production action
Q3-VA-002 | High | High | Backend dependency baseline contained 34 advisory records across nine packages. | pip-audit before/after records. | Updated FastAPI/Pydantic/SuperTokens/Motor/PyMongo/multipart/mail/AWS dependencies and removed unused python-jose. | Deployed tree reduced 34 to one advisory. Running image versions were inspected directly; 32 deployed-image tests and acceptance passed. | Closed in production; one residual tracked in Q3-VA-003
Q3-VA-003 | High | High | cryptography 49.0.0 has PYSEC-2026-3552; fixed in 50.0.0. Current fastapi-mail 1.6.5 requires <50. | Final pip-audit and Trivy backend image scan. | Keep the finding visible; do not force an unsupported resolver override. Track a compatible FastAPI-Mail release or replace the mail abstraction, then upgrade and retest OTP/invitation/password-reset mail. | Final audit still reports exactly one known backend dependency finding. | Open — dependency/vendor
Q3-VA-004 | High | High | Frontend production dependency audit initially returned four vulnerabilities. | npm audit before/after. | Applied supported lockfile remediation. | Current production-branch full/production-only npm audit: 0; deployed frontend Trivy: 0; production build passed. | Closed — verified in production
Q3-VA-005 | High | Medium | Production Compose stored default database credentials and a placeholder application secret in tracked configuration. A tracked value must be treated as exposed even if access is network-restricted. | Compose review and tracked-source scan. | Replaced values with mandatory deployment variables, added a non-secret production template, and retained loopback-only database bindings. Existing values were moved to the untracked production environment during deployment without disclosure. | Production Compose has no tracked defaults and database bindings are loopback-only. Actual credential rotation remains pending. | Deployment closed; credential rotation open
Q3-VA-006 | Medium | High | Production OpenAPI schema was publicly accessible at /api/v1/openapi.json (HTTP 200). | Original public GET on 11 August 2026. | Disabled Swagger, ReDoc and OpenAPI when ENVIRONMENT=production; retained them in non-production environments. | Direct post-deployment public retest on 12 August returned HTTP 404. | Closed — verified in production
Q3-VA-007 | Medium | High | Production backend Compose used a source bind mount and Uvicorn --reload, increasing mutable-code and development-runtime exposure. | Compose review. | Removed the bind mount and reload mode; production image now runs copied code with four non-root workers. | Direct container inspection confirmed appuser, no backend mounts, four Uvicorn workers, healthy state and zero restarts. | Closed — verified in production
Q3-VA-008 | Medium | High | Latest OCI CIS check 5.2.14 reports that only strong SSH MAC algorithms are not enforced. | OCI managed scan completed before the final release: 17 pass, 1 fail. | Direct sshd -T now shows key-only authentication and only hmac-sha2-512-etm, hmac-sha2-256-etm, and umac-128-etm; configuration syntax and a second direct SSH session passed. | Trigger/review a fresh OCI CIS scan to reconcile the managed score before closure. | Open — managed rescan/reconciliation
Q3-VA-009 | Medium | High | The inner frontend NGINX response lacked several browser defense headers; the first deployment also exposed an NGINX add_header inheritance gap on the app shell. | Public/inner header captures and active NGINX configuration. | Added and deployed nosniff, SAMEORIGIN, strict-origin referrer policy and restrictive permissions policy, explicitly repeating them in the index.html location. | Commit bdb03b5, workflow 31539611417; inner and public app-shell responses now contain all four headers plus public HSTS/CSP. | Closed — verified in production
Q3-VA-010 | Medium | High | SuperTokens Python SDK remediation requires CDI 5.4; core 11.0 supports only through CDI 5.3. | Reproduced signup failure after SDK update. | Pinned and deployed SuperTokens core 11.3.7, which supports CDI 5.4. Avoided 12.0 because direct 11.0-to-12.0 local upgrade did not migrate one schema column correctly. | Production backups passed; core 11.3.7 is running and the deployed failed-login acceptance passed. | Closed — verified in production
Q3-VA-011 | Medium scanner / Low confidence | Low | Bandit B608 matched string interpolation in OCI Object Storage URL construction as possible SQL injection. | app/services/s3_service.py, URL-generation function. | Reviewed manually: the code constructs an HTTPS object URL and executes no SQL. | No SQL API or database call exists in the matched function. | Closed — false positive
Q3-VA-012 | Low | High | Bandit reported ten swallowed-exception patterns (B110/B112). | Final Bandit scan. | Retain as code-quality backlog; no direct exploit path was established. Add structured logging when these paths are next modified. | No High-severity Bandit findings. | Open — engineering backlog
Q3-VA-013 | Critical/High scanner records | Medium | Deployed backend image has 4 Critical and 20 High records. Four Critical and 19 High OS records have no vendor fixed version; the only fixable High is Q3-VA-003. | Fresh Trivy scan of actual production docker-backend:latest on 12 August: 4 Critical, 20 High, 56 Medium, 66 Low, 33 Unknown. | Supported Debian 13/Python base, available OS upgrades and reduced build/runtime tooling are deployed. Re-scan when Debian or dependency fixes publish; evaluate distroless only through a separately tested architecture change. | Production scan reproduced the expected result: no fixable Critical and one constrained fixable High. | Open — vendor monitoring; production verified
Q3-VA-014 | Informational/pass | High | Frontend runtime image has no detected vulnerabilities. | Fresh Trivy scan of actual deployed docker-frontend:latest on 12 August. | Updated Node build stage, NGINX runtime and Alpine packages. | 0 Critical, High, Medium or Low records; current production-branch npm audit also returns 0. | Informational/pass — production verified
Q3-VA-015 | Medium accepted exposure | High | Public TCP 22 remains reachable. | Independent external connection check. | SSH is key-only, Fail2ban is enabled, and OCI Bastion is staged. Keep public SSH only until a tested Bastion cutover is approved. | TCP 22, 80, 443 reachable; 3567, 5173, 5432, 8000, 8520 and 27017 filtered/unreachable. | Accepted/monitored; cutover pending
Q3-VA-016 | Informational/pass | High | TLS, redirect, CORS and unsafe method baseline is strong. | Public curl/OpenSSL checks. | No change required in this branch. | HTTP redirects to HTTPS; HTTP/2 200; TLS 1.0/1.1 rejected; TLS 1.2/1.3 accepted; untrusted CORS rejected; TRACE/PUT/DELETE return 405. | Informational/pass
Q3-VA-017 | Informational/pass | High | No secret was detected in tracked source at assessment or post-release retest time. | Gitleaks 8.30.1 against an archive of deployed commit bdb03b5. | Continue secret scanning and rotate any credential ever committed regardless of scanner result. | Fresh post-release tracked-source scan: 0 findings. | Informational/pass — production commit verified
Q3-VA-018 | High operational | High | The OCI host currently has 23 upgradable packages, including Docker/containerd, NGINX, AppArmor and cloud-init components. | Direct apt-get -s upgrade on 12 August 2026. | Assess release notes, create/reconfirm backups, apply in an approved host-maintenance window and complete service/reboot/retest decisions. | Pending maintenance. | Open — production action
Q3-VA-019 | Repository/default-branch alerts | High | GitHub reports 24 open npm Dependabot alerts on the default-branch lockfile: 1 Critical, 12 High, 10 Medium, 1 Low. This differs from the assessed production branch. | GitHub Dependabot API and current production-branch npm audit. | Synchronize/triage the default branch. Do not misstate these alerts as deployed-image findings: production-branch npm audit and deployed frontend Trivy both return zero. | Pending default-branch synchronization/closure. | Open — repository governance